## Product Backlog (Scrum)
MoSCoW ID | Product Backlog ID | Source | Priority (M/S/C/W) | User Story ID | User Story Name | User | Scrum Team Assigned | Complexity | Risk/ Impact | R | Business Process | Type | Primary Actors | Secondary Actors | Comments | Acceptance Criteria | Completeness Criteria | User Acceptance Test Case ID | Comments
1 | 1 | Standard document | High | OnlineWallet:001 | Design Documentation for Backend application | Nandish | Kunal | Average | Low |  | RD:Business Requirement Doc | Non-Functional |  |  |  |  | 22 hrs | Design is fullfilled agaist Business requirement
2 | 2 | Standard document |  | OnlineWallet:002 | Test Plan | Nandish | Kunal |  | Low |  | RD:Business Requirement Doc | Non-Functional |  |  |  |  | 8 hrs | Check the test case is fullfiled with user accepance criteria document
3 | 3 | Standard document | High | OnlineWallet:003 | Bootstrapping the project | Nandish | Kunal | Simple | Low |  | RD:Business Requirement Doc | Non-Functional |  |  |  |  | 4 hrs | Checking Against the Application Setup and ensure the equired dependencies and run the main code and check the server is tarted without errors
4 | 4 | Work session | High | OnlineWallet:004 | Entity Class and TableDEsign and Populating the data | Nandish | Kunal | Complex | Low |  | RD:Business Requirement Doc | Functional |  |  |  |  | 8 hrs | Checking against the Table design in RD
5 | 5 | Work session | High | OnlineWallet:005 | Resgitering user: basic details to be filled by the user | Nandish | Kunal | Average | Low |  | RD:Business Requirement Doc | Functional |  |  |  |  | 10 hrs | TC_Service_01,TC_DAO_01, TC_UI_01
6 | 6 | Work session | High | OnlineWallet:006 | Logging in: email id and password required | Nandish | Kunal | Complex | Low |  | RD:Business Requirement Doc | Functional |  |  |  |  | 16 hrs | TC_Service_02,TC_DAO_02, TC_UI_03
7 | 7 | Work session | High | OnlineWallet:007 | Adding the money from bank account to the wallet | Nandish | Kunal | Simple | High |  |  | Functional |  |  |  |  | 12 hrs
8 | 8 | Work session | High | OnlineWallet:008 | Sending the money to the other wallet account user | Nandish | Kunal | Complex | High |  |  | Functional |  |  |  |  | 21 hrs
9 | 9 | Work session | High | OnlineWallet:009 | Show Balance from user's account | Nandish | Kunal | Complex | High |  |  | Functional |  |  |  |  | 15 hrs
10 | 10 | Work session | High | OnlineWallet:010 | Admin login | Nandish | Kunal | Simple | Low |  |  | Functional |  |  |  |  | 8 hrs
11 | 11 | Work session | High | OnlineWallet:011 | Fetching the userlist of active and nonactive user | Nandish | Kunal | Average | High |  |  | Functional |  |  |  |  | 12 hrs
12 | 12 | Work session | Low | OnlineWallet:012 | Changing the user status of user from active to nonactive and vice versa | Nandish | Kunal | Complex | High |  |  | Functional |  |  |  |  | 20 hrs
Sprint 2 | Sprint 2
13 | 13 | Standard document | High | OnlineWallet:013 | Design Documentation fo Angular application | Sreenath | Kunal | Complex | Low | RD): Business Requirement DOc | RD: Business Requirement and User accepatance Criteria | Non Functional
14 | 14 | Standard document | High | OnlineWallet:014 | Test Plan | Sreenath | Kunal |  | Low |  |  | Non Functional
15 | 15 | Work session | High | OnlineWallet:015 | Design Home page | Sreenath | Kunal | Simple | High |  |  | Functional |  |  |  |  | 15 hrs
16 | 16 | Work session | High | OnlineWallet:016 | Design Register page | Sreenath | Kunal | Simple | Medium |  |  | Functional |  |  |  |  | 10 hrs
17 | 17 | Work session | High | OnlineWallet:017 | Creating Add money page | Sreenath | Kunal | Simple | High |  |  | Functional |  |  |  |  | 6 hrs
18 | 18 | Work session | High | OnlineWallet:018 | Creating a Transfer Money page | Sreenath | Kunal | Average | High |  |  | Functional |  |  |  |  | 8 hrs
19 | 19 | Work session | High | OnlineWallet:019 | Creating Show Balance page | Sreenath | Kunal | Simple | Low |  |  | Functional |  |  |  |  | 6 hrs
20 | 20 | Work session | Low | OnlineWallet:020 | Design Admin login page | Sreenath | Kunal | Simple | High |  |  | Functional |  |  |  |  | 15 hrs
21 | 21 | Work session | Low | OnlineWallet:021 | Design View User page | Sreenath | Kunal | Complex | High |  |  | Functional |  |  |  |  | 15 hrs
22 | 22 | Work session | Low | OnlineWallet:022 | Added Logout Fucntionality for User and Admin | Sreenath | Kunal | Average | High |  |  | Functional |  |  |  |  | 15 hrs
28 | 30
29 | 31
30 | 32
33
31 | 34
32 | 35
33 | 36
34 | 37
35 | 38
36 | 39
37 | 40
38 | 41
39 | 42
40 | 43
41 | 44
42 | 45
43 | 46
44 | 47
45 | 48
46 | 49
When using a Scrum approach to project management, use this sheet to document the Product Backlog, as captured in User Stories.
Note on A3: This column is used to Link back to the Full MoSCoW list for the project (RD.045 sheet).
Note on B3: This column is used to uniquely identify each row on this worksheet. User Stories in a given Sprint are traced back to the Product Backlog using the User Story ID to the details on the Sprint Backlog
Note on C3: This column documents the source from which the expanded requirement came (e.g., statement of work, change request, work session, standards document etc.).
Note on D3: Column to prioritize requirements using MoSCoW) - Must Have, Should Have, Could Have, Won't Have
Note on E3: Column for uniquely identifying the use case, Originates from Use case Model [RA.023] When used Corresponds to a use case number on the Use Case Catalog sheet. Note - Requirements satisfied by COTS applications that are defined in SOW are assigned a use case in order to create traceability. Not required for requirements satisfied by the COTS App that are not in SOW.
Note on F3: Brief description of the requirements necessary to fulfill the objective
Note on G3: Column used to identify owner of requirement as defined by SOW and/or supporting documentation. Defined assumptions are treated as requirements owned by designated party.
Note on H3: Column used to identify owner of requirement as defined by SOW and/or supporting documentation. Defined assumptions are treated as requirements owned by designated party.
Note on I3: Complexity of the functional requirement. Very Simple Simple Average Complex Very Complex
Note on J3: Technical, Organizational, External project risk associated with the requirement. This is further detailed in the Project Risk Management Plan. What is the probability that something will go wrong in meeting the requirement? A risk might happen, or it might not; there is some uncertainty. Use H (High), M (Medium), L (Low).
Note on K3: Used if reference is needed to another work product that provides further detail of the requirement. Examples include RA.027 Candidate Business Rules, RA.090 Reporting Fit Analysis, RA.027 Use Case Details, RD.070 Audit and Control Requirements), DS.030 Application Set-up Documents.
Note on L3: Column to document the originating process where the process is defined and necessary. For example, a process that originates from either Current Process Model [RD.030] or Future Process Model [RD.011].
Note on M3: Defines whether the User Story is Functional, Non-Functional or Technical type.
Note on N3: Column provides linkage to primary actors defined in RA.023 (Use Case Model) and/or RD.005 (System Context Diagram)
Note on O3: Column provides linkage to secondary actors defined in RA.023 (Use Case Model) and/or RD.005 (System Context Diagram)
Note on P3: Use column for supporting comments.
Note on Q3: Column for defining the agreed upon acceptance criteria
Note on R3: Description of the condition(s) that indicate the requirement has been satisfied.
Note on S3: This column is used to link the User Story to the User Acceptance test scenarios that validate the requirement was satisfied.
Note on T3: This column is used to provide supporting information, such as changes to the original requirement.

## Sprint Backlog 2
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
15 | OnlineWallet: 013 | 1 | Wireframes and story boarding for each task | Kunal | 2020-04-27 | 2 hrs | 1 hr | Completed
|  | 2 | Routing Url List | Arushi | 2020-04-27 | 2 hrs | 2 hrs | Completed
|  | 4 | Angular service | Kunal | 2020-04-27 | 3 hrs | 2 hrs | Completed
|  | 5 | Components details | Arushi | 2020-04-27 | 2 hrs | 3 hrs | Completed
|  | 6 | Detail about the security | Kunal | 2020-04-27 | 3 hrs | 2 hrs | Completed
16 | OnlineWallet: 015 | 1 | Designin Login Page | Arushi | 2020-04-28 | 4 hrs | 3 hrs | Completed | 4 hrs
|  | 2 | Component sends the email and pasword to Login service | Arushi | 2020-04-28 | 5 hrs | 4 hrs | Completed | 7 hrs
|  | 3 | Loginservice class confirms the user through backend and gets the userId | Arushi | 2020-04-28 | 6 hrs | 5 hrs | Completed | 6 hrs
17 | OnlineWallet: 016 | 1 | Design a signup form that captures the details of users | Arushi | 2020-04-27 | 3 hrs | 4 hrs | Completed | 6 hrs
|  | 2 | Component sends the details to registerUser service | Arushi | 2020-04-27 | 3 hrs | 3 hrs | Completed | 5 hrs
|  | 3 | Angular service make the webservice call and saves the data of the new user in database with the help of backend application | Arushi | 2020-04-27 | 3 hrs | 3 hrs | Completed | 3 hrs
| OnlineWallet: 017 |  | Designing of Add money page to ask for mode of payement(dummy) and amount to add to his wallet | Arushi |  |  |  | Completed
|  |  | The component will send the amount to addamount service | Arushi |  |  |  | Completed
|  |  | Service send the data to application and application will add the amount in user's balance | Arushi |  |  |  | Completed
| OnlineWallet: 018 |  | Designing of Transfer money page to ask for beneficiary email address and amount to transfer amount | Kunal |  |  |  | Completed
|  |  | the component will send the amount to tranfermoney service | Kunal |  |  |  | Completed
|  |  | Service will send the email and amount to verify if the beneficary exist and if true then add the amount to the benefeciary's balance and deduct from user's balance | Kunal |  |  |  | Completed
| OnlineWallet: 019 |  | Designing of show balance page to only display the balance of from user's account | Kunal |  |  |  | Completed
|  |  | the component will fetch the balance from the application on intialization and show the balance | Kunal |  |  |  | Completed
18 | OnlineWallet: 020 | 1 | Designin Admin Login Page to take the Admin username and password | Arushi | 2020-05-01 | 4 hrs | 3 hrs | Completed | 4 hrs
|  | 2 | Component sends the email and pasword to Loginservice | Arushi | 2020-05-01 | 5 hrs | 4 hrs | Completed | 7 hrs
|  | 3 | Loginservice class confirms the admin through backend and stores the adminid returned | Arushi | 2020-05-01 | 6 hrs | 5 hrs | Completed | 6 hrs
19 | OnlineWallet: 021 | 1 | Designning a View user page for admin to activate and deactivate accounts | Kunal | 2020-05-01 | 10 hrs | 10 hrs | Completed | 12 hrs
|  | 2 | view user component show two tables for active and non active users by getting list of emails from get-user service. Controls are activate and deactivate. Sends the email address to change-status service | Kunal | 2020-05-01 | 15 hrs | 12 hrs | Completed | 15 hrs
|  | 3 | change status service will send the email and status to backend application to change the user status to active or no active | Kunal | 2020-05-01 | 8 hrs | 6 hrs | Completed | 8 hrs
| OnlineWallet: 020 |  | Adding the logout features which will logs out the user or admin from the system | Kunal |  |  |  | Completed
|  |  | added routing guard so that no user can access service without logging in | Kunal |  |  |  | Completed
List User Story steps that were not completed at Sprint End
When using a Scrum approach to project management, this worksheet is intended to capture the detail tasks of User Stories for the current Sprint.
Note, this is further detail of the user stories that appear on the Product Backlog sheet.
Note on A3: This column is used to trace each row of this spreadsheet back to a specific row on the MoSCoW List worksheet.
Note on B3: This column is used to document the Use Case Identifier.
Note on D3: Task Step description. You would only use this column when detailing User Stories using the short form as described in RA.021. If you are using the long form of the User Stories template you may eliminate this column.
Note on E3: List the Scrum team members assigned to this task.
Note on F3: Column is used to document the date the task was assigned
Note on G3: Use this column to provide Initial Scrum team estimate of effort for the task step to be completed, may be numbers of days or hours.
Note on H3: Adjusted estimate after the Sprint has begun
Note on I3: Task status: Started In Progress Completed Cancelled Deferred to Sprint <Sprint number>
Note on J3: Actual Effort - after the step has been completed a number indicating how many hours or days. This number will be used to prepare the burndown chart.
Note on K3: Use this column to provide supporting information such as changes to the original requirement.
Note on M3: This column is used to link the requirements to any resulting modules (software).
Note on N3: This column is used to link the requirements/use cases to the test scenarios.
Note on O3: This column is used to link the requirements/use cases to the test scenarios.
Note on P3: This column is used to link the requirements/use cases to the test scenarios.

## Sprint Backlog 1
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate (in hours) | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
1 | OnlineWallet:001 | 1 | Entity Class Design | Kunal | 2020-02-14 | 4 | 2 |  | 3
|  | 2 | Table Design | Kunal | 2020-02-14 | 2 | 2 |  | 2
|  | 3 | Application Architecture | Kunal | 2020-02-14 | 2 | 1 |  | 2
|  | 4 | Use case diagram | Arushi | 2020-02-14 | 2 | 2 |  | 3
|  | 5 | Sequence Diagram | Arushi | 2020-02-14 | 4 | 3 |  | 3
|  | 6 | Each use case detail description | Arushi | 2020-02-14 | 4 | 4 |  | 5
|  | 7 | Class Layer diagram | Arushi | 2020-02-14 | 1 | 2 |  | 2
|  | 8 | Class Diagram | Arushi | 2020-02-14 | 2 | 2 |  | 3
|  | 9 | Webservice URL Details | Kunal | 2020-04-14 | 1 | 1 |  | 1
2 | OnlineWallet:002 | 1 | Table Design | Kunal | 2020-04-17 | 2 | 2 |  | 2
|  | 2 | Application Architecture | Kunal | 2020-04-17 | 2 | 1 |  | 2
|  | 3 | Use case diagram | Arushi | 2020-04-17 | 2 | 2 |  | 3
3 | OnlineWallet:003 | 1 | Creating a Spring boot starter project | Kunal | 2020-04-17 | 2 | 1 | Completed | 1
|  | 2 | Adding dependencies in Pom.xml and initializing it | Kunal | 2020-04-17 | 1 | 1 | Completed | 1
|  | 3 | Adding server, jpa properties in application.properties | Kunal | 2020-04-17 | 2 | 1 | Completed | 2
4 | OnlineWallet:004 | 1 | Entity Class Design | Kunal | 2020-04-17 | 4 | 2 | Completed | 3
|  | 2 | Check tables are populated in DB | Arushi | 2020-04-20 | 3 | 2 | Completed | 3
|  | 3 | Populate the Data | Arushi | 2020-04-20 | 3 | 4 | Completed | 3
5 | OnlineWallet:005 | 1 | Register method which will take the user data entered from user in frontend | Arushi | 2020-04-17 | 3 | 2 | Completed | 2
|  | 2 | Rest controller method to take the details in object form also containig the url with mapping anotation | Arushi | 2020-04-17 | 2 | 3 | Completed | 3
|  | 3 | Service method check the data wheather it is correct or not otherise throw exception | Arushi | 2020-04-17 | 3 | 4 | Completed | 4
|  | 4 | Dao method contains the entitymanager which persist the data in database | Arushi | 2020-04-17 | 3 | 4 | Completed | 5
6 | OnlineWallet:006 | 1 | Login method which will conduct the login criteria by taking data from user | Arushi | 2020-04-21 | 5 | 7 | Completed | 15
|  | 2 | Rest Controller method to take the details and also containig the url with mapping anotation | Arushi | 2020-04-21 | 2 | 3 | Completed | 5
|  | 3 | Service method check the data wheather it is correct or not by comparing it from database otherise throw exception | Arushi | 2020-04-21 | 3 | 3 | Completed | 6
|  | 4 | Dao method contains the entitymanager which will take help from jpql for verification | Arushi | 2020-04-21 | 2 | 4 | Completed | 6
7 | OnlineWallet:007 | 1 | Add money method which will enable users to add money to their Wallet | Arushi | 2020-04-24 | 9 | 14 | Completed | 15
|  | 2 | Rest Controller method to link the work of service with help of anotations | Arushi | 2020-04-24 | 4 | 7 | Completed | 5
|  | 3 | Service method contains call to dao method fetching the user and saving the new updated incremented balance | Arushi | 2020-04-24 | 5 | 6 | Completed | 4
8 | Online Wallet:008 | 1 | Send Money method which will help users to transfer funds from one wallet account to another | Kunal | 2020-04-20 | 3 | 1.5 | Completed | 2.5
|  | 2 | Rest Controller method to take the details and also containig the url with mapping anotation | Kunal | 2020-04-22 | 2 | 2 | Completed | 2
|  | 3 | Service method check the data wheather it is correct or not by comparing it from database otherise throw exception | Kunal | 2020-04-22 | 2 | 2.5 | Completed | 3
|  | 4 | Dao method contains the entitymanager which will take help from jpa query to take the list of the users | Kunal | 2020-04-22 | 1 | 1.5 | Completed | 2
9 | OnlineWallet: 009 | 1 | Show Balance method which helps users to check the balance in their wallet account. | Kunal | 2020-04-20 | 3 | 1.5 | Completed | 4
|  | 2 | Rest Controller method to take the details and also containig the url with mapping anotation | Kunal | 2020-04-23 | 2 | 2 | Completed | 3
|  | 3 | Service method check the data wheather it is correct or not by comparing it from database otherise throw exception | Kunal | 2020-04-23 | 2 | 1.5 | Completed | 2
|  | 4 | Dao method contains the entitymanager which will take help from jpa query to take the list of the users | Kunal | 2020-04-24 | 1 | 1.5 | Completed | 3
10 | OnlineWallet:010 | 1 | AdminLogin method which will take the Admin data entered from user in frontend | Arushi | 2020-04-20 | 3 | 1.5 | Completed | 4
|  | 2 | Rest controller method to take the details also containig the url with mapping anotation | Arushi | 2020-04-21 | 2 | 2 | Completed | 3
|  | 3 | Service method check the data wheather it is correct or not otherise throw exception | Arushi | 2020-04-21 | 2 | 1.5 | Completed | 3
|  | 4 | Dao method contains the entitymanager which will take help from jpql for verification | Arushi | 2020-04-22 | 1 | 1.5 | Completed | 2
11 | OnlineWallet:011 | 1 | userlist method which will show the email list of the users based on their status | Kunal | 2020-04-22 | 5 | 7 | Completed | 15
|  | 2 | Rest Controller method to take the details and also containig the url with mapping anotation | Kunal | 2020-04-23 | 2 | 3 | Completed | 5
|  | 3 | Service method check the data wheather it is correct or not by comparing it from database otherise throw exception | Kunal | 2020-04-24 | 3 | 3 | Completed | 6
|  | 4 | Dao method contains the entitymanager which will take help from jpa query to return the list of the users | Kunal | 2020-04-24 | 2 | 4 | Completed | 6
12 | Online Wallet:012 | 1 | changestatus method which will change the user's status to active or non active | Kunal | 2020-04-20 | 3 | 2 | Completed | 2
|  | 2 | Rest Controller method to take the details and also containig the url with mapping anotation | Kunal | 2020-04-20 | 2 | 3 | Completed | 3
|  | 3 | Service method check the data wheather it is correct or not by comparing it from database otherise throw exception | Kunal | 2020-04-21 | 3 | 4 | Completed | 4
|  | 4 | Dao method contains entitymanager method to fetch the use | Kunal | 2020-04-21 | 3 | 4 | Completed | 5
List User Story steps that were not completed at Sprint End
When using a Scrum approach to project management, this worksheet is intended to capture the detail tasks of User Stories for the current Sprint.
Note, this is further detail of the user stories that appear on the Product Backlog sheet.
Note on A3: This column is used to trace each row of this spreadsheet back to a specific row on the MoSCoW List worksheet.
Note on B3: This column is used to document the Use Case Identifier.
Note on D3: Task Step description. You would only use this column when detailing User Stories using the short form as described in RA.021. If you are using the long form of the User Stories template you may eliminate this column.
Note on E3: List the Scrum team members assigned to this task.
Note on F3: Column is used to document the date the task was assigned
Note on G3: Use this column to provide Initial Scrum team estimate of effort for the task step to be completed, may be numbers of days or hours.
Note on H3: Adjusted estimate after the Sprint has begun
Note on I3: Task status: Started In Progress Completed Cancelled Deferred to Sprint <Sprint number>
Note on J3: Actual Effort - after the step has been completed a number indicating how many hours or days. This number will be used to prepare the burndown chart.
Note on K3: Use this column to provide supporting information such as changes to the original requirement.
Note on M3: This column is used to link the requirements to any resulting modules (software).
Note on N3: This column is used to link the requirements/use cases to the test scenarios.
Note on O3: This column is used to link the requirements/use cases to the test scenarios.
Note on P3: This column is used to link the requirements/use cases to the test scenarios.